## 1003DC
- Observer's Report Sercel SN388 -
CLIENT: NORANDA MINING & EXPLORATION | AREA: BRUNSWICK 3D | DATE: OCT. 03, 2000
CONTRACTOR: WESTERN GEOPHYSICAL CREW NO: 716 B JOB NO: 00-017 OBSERVERS: MITSCHKE / MARTIN
=====================================================================================================================
WEATHER: CLEAR, LIGHT WINDS |  |  | TEMP.: 15 C.
*********************************************************************************************************************
6:30 TO 7:00 - ARRIVED IN FIELD.
7:01 TO 7:30 - POWER UP, INITIAL LINE CHECKS, LINE PROBLEMS ON R-30.
7:31 TO 8:00 - CREW ARRIVED IN FIELD, RAN MORNING TESTS, CAP SIMS.
8:01 TO 9:09 - SHOOTERS MOVING INTO POSITION, FIXING LINE PROBLEMS, HELICOPTER SLINGING BAGS.
9:10 TO 10:00 - START PRODUCTION.
10:01 TO 1:05 - RECORDER MOVING TO NEW SET UP, HELICOPTER SLINGING EQUIPMENT BAGS.
2:25 TO 4:00 - CONTINUE PRODUCTION.
4:01 TO 5:30 - HELICOPTER ON SPREAD.
5:31 TO 6:45 - CONTINUE PRODUCTION.
6:46 TO 7:30 - FINISHING COMMENTS, DRIVE TO TOWN.
*********************************************************************************************************************
NOISE EVIDENT ON RECORDS ON R-28 @ STATIONS 1001 TO 1015 CAUSED BY HEAVY EQUIPMENT WORKING
AT BRIDGE SITE.
TRAFFIC NOISE EVIDENT ON RECORDS WHERE HIGHWAY #430 CROSSES AND PARRALLELS RECEIVER LINES.
GRAVEL TRUCKS AND LOGGING TRUCKS HAULING ALONG HAUL ROAD CREATING NOISE THROUGH THE RECORDS.
*RECEIVER LINE 28 - STATION 1040 TO 1042 DEAD STATION DUE TO SWAMP.
*RECEIVER LINE 44 - STATION 1154 DEAD STATION DUE TO SWAMP.
*RECEIVER LINE 48 - STATIONS 1187 TO 1192 AND 1202, DEAD STATIONS DUE TO SWAMP.
*********************************************************************************************************************
SOURCES SHOT ON TODAY: | [6 empty] | SWATHS COMPLETED: 19, 20, 21
|  |  | S-1 - 1054 TO 1050 |  |  | S-17 - 1079 TO 1074
|  |  | S-3 - 1057 TO 1052 |  |  | S-19 - 1082 TO 1078
|  |  | S-5 - 1060 TO 1056 |  |  | S-21 - 1085 TO 1081
|  |  | S-7 - 1069 TO 1059 |  | S-23 - 1088 TO 1084
|  |  | S-9 - 1077 TO 1062 |  |  | S-25 - 1091 TO 1087
|  | S-11 - 1080 TO 1065 |  |  | S-27 - 1094 TO 1090
|  | S-13 - 1083 TO 1068 |  |  | S-29 - 1097 TO 1093
S-15 - 1076 TO 1071
*********************************************************************************************************************
EXTRA CAP USED ON S-29/S.P.-1097
FILE 642 - S-1/1054 RECEIVER LINES 32 TO 48 DROPPED T=1.36 SECONDS.
FILE 644 - S-1/1052 RECEIVER LINE 46 DROPPED OUT AT T=1.21 SECONDS.
FILE 652 - S-15/1074 RECEIVER LINE 46 DROPPED OUT AT T=0 SECONDS.
FILE 664 - S-17/1077 RECEIVER LINE 46 DROPPED OUT AT T=0 SECONDS.
FILE 666 - S-13/1068 RECEIVER LINE 46 DROPPED OUT AT T=1.70 SECONDS.
FILE 671 - S-13/1069 RECEIVER LINE 46 DROPPED OUT AT T=1.30 SECONDS.
FILE 688 - S-15/1058 RECEIVER LINES 34 TO 48 DROPPED OUT AT @ T=1.77 SECONDS.
FILE #607 - S-13/1082 - CAP ONLY, PRIMA CORD ONLY.
FILE #620 - S-11/1078 - CAP ONLY, PRIMA CORD ONLY.
FILE #629 - S-9/1072 - CAP ONLY, PRIMA CORD ONLY.
FILE #667 - S-3/1055 - CAP ONLY, PRIMA CORD ONLY.
FILE #669 - S-27/1090 - CAP ONLY, PRIMA CORD ONLY.
***PLEASE OMIT FILE 645, S.P.-1097/S-29, CAP ONLY.
*********************************************************************************************************************
CAP SIMS; FILES: 601 TO 604 | FIRST PRODUCTION FILE: 605 |  | LAST PRODUCTION FILE: 722
FIRST S.P. FOR THE DAY: S- 13/1083 |  | LAST S.P. FOR THE DAY: S- 23/1084
TOTAL DETONATORS USED FOR PRODUCTION: 117 |  |  | TOTAL DETONATORS USED FOR BRUNSWICK 3D: 687
EXTRA DETONATORS USED: 020 |  |  |  | TOTAL CAP SIM FILES: 022
OMIT FILES TODAY: 001 |  | TOTAL OMIT FILES: 013
TOTAL PROFILES FOR THE DAY: 117 |  |  | TOTAL PROFILES ON BRUNSWICK 3D: 687
TOTAL TRAVEL TIME: 1.0 HRS FIELD TIME: 12.0 HRS SAFETY MEETING: 0.0 HRS TOTAL CHARGEABLE HRS: 13.0 HRS